## Sheet1
ID | Story | Sprint | Priority | Status | Points
1 | As a student, I need to know which elective courses meet general education requirements. | 1 | H | W | 5
2 | As a busy student, I need difficulty analyzer for my schedule so I don’t get in over my head. | 1 | L | W | 8
3 | As a picky student, I need a professor evaluator so I know which professors will help me succeed. | 1 | L | W | 8
4 | As a student with a busy schedule, I need to be able to specify which times I would like classes to be at. | 1 | H | W | 1
5 | As a student with specific interests, I need an application which allows me to search/filter courses based on course number. | 1 | H | W | 4
6 | As a student with specific interests, I need an application which allows me to search/filter courses based on course difficulty. | 1 | H | W | 2
7 | As a student with specific interests, I need an application which allows me to search/filter courses based on course title. | 1 | H | W | 2
8 | As a student with specific interests, I need an application which allows me to search/filter courses based on course professor. | 1 | H | W | 2
9 | As a student, I need suggestions on which classes I should take to work on my degree. | 1 | M | W | 8
10 | As a student with many interests, I would like to know how best to introduce secondary majors into my schedule. | 1 | M | W | 4
11 | As a student with many interests, I would like to know how to best introduce additional minors into my scheule | 1 | M | W | 2
12 | As a transfer student, I need to add courses I took at my sending school to my degree progress. | 1 | H | W | 2
13 | As a prospective or incoming student, I need to be able to browse the course catalogue. | 1 | H | W | 10
14 | As a prospective or incoming student, I would like to browse sample degree plans. | 1 | M | W | 4
15 | As a returning student, I would like to compare my degree progress with sample degree plans. | 1 | L | W | 4
16 | As a curious student, I’d like to see course descriptions about unfamiliar courses. | 1 | M | W | 2
17 | As a curious student, I’d like to be notified of new course additions so that I am aware of my choices. | 1 | L | W | 2
18 | As a student, I need to be able to visualize the prerequisites for courses I wish to take. | 1 | H | W | 4
19 | As a student, I need to be able to view my schedule. | 1 | H | W | 10
20 | As a busy student, I’d like to color code my schedule by difficulty. | 1 | L | W | 1
21 | As a busy student, I’d like to color code my schedule by major. | 1 | L | W | 1
22 | As a recurring user, I’d like to be able to share my schedule from the website with friends and family. | 1 | L | W | 2
23 | As a recurring user, I need a way to export my schedule that I created so I can see it outside of the application. | 1 | M | W | 1
24 | As a student, I would like to print off my planned schedule for ease of access. | 1 | L | W | 2
25 | As a user with several devices, I’d like to access my degree plan on several devices. | 1 | L | W | 8
26 | As a user, I’d like to import course plans made by other people. | 1 | L | W | 2
27 | As a user, I’d like to be able to export my degree plan to share with my friends. | 1 | L | W | 2
28 | As a disorganized person, I need an application that will save my schedule between semesters so I don’t lose track of my long term plan. | 1 | H | W | 2